## Home
Technical Query |  |  |  | AKM MEADVILLE
Customer Code | Customer P/N |  |  | AKMMV Site | Vendor P/N | Prepared by / Date
QAL01 | 25-PE319-P1 REV A |  |  | SME | DAQHIW10M906A02 | YXY ¦ 11/20/2025
Issue # | Status | Design Review Findings | AKMMV Recommendations | Customer Response | By whom/Date | Links
1 | Closed | 1. According to actual Cuts in Gerber, the dielectric thickness will be a little different from original value. Please see the picture for our proposed stack-up. 2. To meet the value of impedance, we properly adjusted the width/space of some impedance lines, please see link for example. | 1. Propose to follow the stackup that our suggestion to build. 2. We propose to follow our adjusted impedance lines width/space to control and build. | 1. Approved 2. Approved | Boobeshchandar / 20-11-2025 | Issue 1
2 | Closed | The soldermask opening of NPTH are close to soldermask opening of pad. It is difficult to build soldermask dam. Please see the graphics for example. | Allow to remove solder mask dam, we will add whole solder mask opening for them. | Approved | Boobeshchandar / 20-11-2025 | Issue 2
3 | Closed | Per customer specification, we need to enlarge the solder mask opening size for the solder mask images that are the same size as the pads. We will follow the requirement to enlarge the solder mask opening, and we also suggest to optimize the soldermask opening design by pad balance method to ensure the finished size of these pads to be regular or approximately same. See graphics for example. | We propose to follow the requirement to enlarge the solder mask opening, and we also suggest to optimize the soldermask opening design by pad balance method to ensure the finished size of these pads to be regular or approximately same. | Approved | Boobeshchandar / 20-11-2025 | Issue 3
4 | Closed | Per FAB, the customer required min: 3.8mm clearance from center of fiducial marks, so these fiducial marks are isolated. It's very easy to be peeled off during fabrication. This figure is not for this project, use other projects for example. | In order to avoid this problem, we would add a circular copper ring (width ≥ 15mil) around the fiducial mark, please refer to the attached figure for other projects. Pls confirm. | Approved | Boobeshchandar / 20-11-2025 | Issue 4
5 | Closed | Some via hole pads are designed near the edge of copper plane. Usually the etching compensation of pads is larger than the copper plane in our CAM system for production. After etching, the pads might exceed the edge of copper plane and then some protrusions exist. See the picture for detail. | Please allow the pads to exceed the edge of copper plane a little. | Approved | Boobeshchandar / 20-11-2025 | Issue 5
6 | Closed | Solids epoxy "PHP-900IR 10F" is not available for us. | We propose "PHP900 MB-10A" material as an alternate. | Approved. Make sure the electrical properties are matching with PHP-900IR 10F. | Boobeshchandar / 20-11-2025 | Issue 6
7 | On Hold | The drawing requires the marks to be placed on the bottom side. But in Gerber, it is placed at the top side. | We propose to follow gerber to build, and UL is also placed at the top side. | Approve to follow the gerber. |  | Issue 7